Project:

- Automatic Mixed-Signal Circuit Layout Optimization and Regeneration

Goal:

12/6/02 - Be able to run Extraction, Optimization, Regeneration, and

Inductor part of one analog layout example (Adam's VCO).  Finish a paper

for DAC.

Weekly Progress:

- Active area (drain/source) resizing code is done.

- Start coding on transistor possible width/length range finder, in order

to input into the synthesis tool.

Next Week Plan:

- Get the synthesis tool, so we can understand the input/output interface.

- Finish coding on possible transistor range, so Sam and I can print the

correct output to the synthesis tool.

- Poly resizing (based on width and length).

- Interfacing code of synthesis output to resizing part.